1. Wednesday, August 28, 2019, 2:00 PM
2. Monday, September 16, 2019, 2:00 PM
3. Monday, September 30, 2019, 2:00 PM
4. Monday, October 7, 2019, 2:00 PM
5. Monday, October 21, 2019, 2:00 PM
6. Monday, November 4, 2019, 2:00 PM
7. Monday, November 18, 2019, 2:00 PM
8. Monday, December 2, 2019, 2:00 PM
9. Monday, December 16, 2019, 2:00 PM

* To Be Completed By: Wednesday, August 28, 2019, 2:00 PM
  + Methodological research into GLMs, and QC
  + Timeline development
  + Speed Talk prep
  + Question development
* To Be Completed By: Monday, September 16, 2019, 2:00 PM
  + Begin official Exploratory Data Analysis, Data Quality Control, and transformations.
  + Begin development of comparison models, ensure theoretical modeling assumptions have been satisfied, and analytic methods correct.
* To Be Completed By: Monday, September 30, 2019, 2:00 PM
  + Continue with data QC and EDA
  + Develop analytic methods:
    - Create theoretical framework for each model type
    - Generate comparisons of theoretical models using developed data sets
  + Begin Abstract
* To Be Completed By: Monday, October 7, 2019, 2:00 PM
  + Finalize data, summary statistics and visualizations
  + Develop and optimize analytic methodologies
  + Refine Abstract
  + Generate initial results
* To Be Completed By: Monday, October 21, 2019, 2:00 PM
  + Finalize analytic methodologies and apply to final data
  + Finalize abstract
* To Be Completed By: Monday, November 4, 2019, 2:00 PM
  + Finalize results
  + Begin composition of discussion
* To Be Completed By: Monday, November 18, 2019, 2:00 PM
  + Finalize discussion
  + Begin composition of Introduction
* To Be Completed By: Monday, December 2, 2019, 2:00 PM
  + Completed rough draft of paper, to be submitted for feedback, corrections, and logistical considerations including thorough consideration of references, etc.
* To Be Completed By: Monday, December 16, 2019, 2:00 PM
  + Final paper submitted, minor corrections, or anticipated submission of paper