1. ~~Wednesday, August 28, 2019, 2:00 PM~~
2. Monday, September 16, 2019, 2:00 PM
3. Monday, September 30, 2019, 2:00 PM
4. Monday, October 7, 2019, 2:00 PM
5. Monday, October 21, 2019, 2:00 PM
6. Monday, November 4, 2019, 2:00 PM
7. Monday, November 18, 2019, 2:00 PM
8. Monday, December 2, 2019, 2:00 PM
9. Monday, December 16, 2019, 2:00 PM
10. To Be Completed By: Wednesday, August 28, 2019, 2:00 PM
    * ~~Methodological research into GLMs, and QC~~
    * ~~Speed Talk prep~~
    * ~~Question development~~
11. To Be Completed By: Monday, September 16, 2019, 2:00 PM
    * Timeline development
    * QC & EDA close to completed
    * Possible Zoom meeting
12. To Be Completed By: Monday, September 30, 2019, 2:00 PM
    * QC & EDA Complete
    * Analysis started on cleaned data
    * Begin:
      + Writing: introduction, visualizations, methodologies,…(anything not dependent on results)
      + presentation construction
13. To Be Completed By: Monday, October 7, 2019, 2:00 PM
    * Finalize: Results
    * Begin:
      + Writing: abstract, results, discussion
      + Presentation rehearsal
    * Revise:
      + Previously writings on intro, methods,… etc.
      + Presentation
14. To Be Completed By: Monday, October 21, 2019, 2:00 PM
    * Completed revisions recommendations on paper & presentation from meeting 4
15. To Be Completed By: Monday, November 4, 2019, 2:00 PM
    * Complete revision recommendations on paper from meeting 5
    * Finalize Presentation
      + Included/excluded content
      + Properly rehearsed
16. STAT GEN PRESENTATION (11/11) (NO MEETING) (DEADLINE)
17. To Be Completed By: Monday, November 18, 2019, 2:00 PM
    * Complete revision recommendations on paper from meeting 6
18. To Be Completed By: Monday, December 2, 2019, 2:00 PM
    * Complete revision recommendations on paper from meeting 7
19. To Be Completed By: Monday, December 16, 2019, 2:00 PM
    * Final paper submitted, minor corrections, or anticipated submission of paper