# Remaining Timeline

#### This document will be updated regularly to reflect the most accurate information possible

## MS Project: Lee Panter

### Document Objectives:

* Set deadlines for outstanding project checkpoints, including:
  + Oral Exam
  + Final draft submission for approval
  + As needed:
    - Revision submissions
    - Initial content submissions
* Provide details regarding submission at each checkpoint
* Keep track of alterations in timeline

## Google Calendar:

I have created a Google Calendar which will reflect all changes, live. If you wish to subscibe: [Google Calendar-LPanterMSProject](https://calendar.google.com/calendar?cid=aHZiOHI1cmEwcGd2MmI0aWk3ZnNsNG1vaGNAZ3JvdXAuY2FsZW5kYXIuZ29vZ2xlLmNvbQ)

## Submission Deadlines and Meetings

* **v1** - Inital Submission **(1/2/2019)**
  + Thursday, January 2nd, 2020
  + To include: Introduction, Methods, Motivating Example, Implementation
  + Version 1 (v1)
  + Sub-versions (small corrections, minor updates: v1.1, v1.2 - if needed)
* Post v1 meeting **(1/7/2020)**
  + Tuesday, January 7th, 2020
  + Discuss additional sections: Abstract, Discussion
  + Intital feedback: (Feedback: v1)
  + *NOTE: the date of this meeting does not allow for 7 days of review time*
* v1 Feedback **1/2/2020 - 1/9/2020**
* **v2** - Initial Submission (with Additional Sections) **(1/14/2020)**
  + Tuesday, January 14th, 2020
  + Make recommended alterations from v1 Feedback
  + Initial submission of additional sections
  + Version (v2)
* v2 Feedback **1/14/2020 - 1/21/2020**
* *Post v2 meeting*
  + Not scheduled, and if advisable
  + Ideal Date Range: **1/21/2020 - 1/24/2020**
* **v3** - Revision Submission **(1/28/2020)**
  + Tuesday, January 28th, 2020
  + Make recommended alterations from v2 Feedback
  + Version (v3)
* v3 Feedback **1/28/2020 - 2/4/2020**
* *Post v3 meeting*
  + Not scheduled, and if advisable
  + Ideal Date Range: **2/4/2020 - 2/7/2020**
* **Final Submission (2/11/2020)**
  + Tuesday, February 11th, 2020
  + Make recommended alterations from v3 Feedback
  + Submission to Advisory Committee
* **Ov1** Initial Oral Presentation Submission **(2/18/2020)**
* *Ov1 Content Review Meeting*
  + Not scheduled, and if advisable
  + Ideal Date Range: **2/18/2020 - 2/21/2020**
* **Ov2** Revised Oral Presentation Submission **(2/25/2020)**
  + Make recommended alterations from Ov1 Meeting
* *Ov2 Review Meeting*
  + Not scheduled, and if advisable
  + Ideal Date Range: **2/25/2020 - 2/28/2020**
  + Content Review and Practice Presentation
* **Ov3** Revised Oral Presentation Submission **(3/3/2020)**
  + Make recommended alterations from Ov3 Meeting
* *Ov3 Review Meeting*
  + Not scheduled, and if advisable
  + Ideal Date Range: **3/3/2020 - 3/6/2020**
  + Practice Presentation (content review if needed)
* **Final Oral Presentation (3/10/2020)** 
  + Tuesday, March 10th, 2020
  + Make recommended alterations from Ov3 Meeting

## Notes:

* The deadlines above allow for:
  + Three revision opportunities (two opportunities for additional sections: Discussion and Abstract)
  + Three Oral Presentation feedback opportunities (at least two chances for content review and at least two chances for presentation practice - if advisable)
* The dates and recurrences of deadlines above have been chosen arbitrarily and are completely flexible. (With exception to v1 - Intial Submission and Post v1 meeting, which have already been scheduled)